Project Specification

Project Name: Calice

Version: 0.1

Approval:

|  |  | name | signature | date |  |
| --- | --- | --- | --- | --- | --- |
|  | Project Manager | Rob Halsall | XXXXXXXXXXX | XXXXXXXXX |  |
|  | Customer/Sponsor | Paul Dauncey | XXXXXXXXXXX | XXXXXXXXX |  |

Distribution:

| Project Manager: | Rob Halsall |
| --- | --- |
| Customer/Sponsor: | Paul Dauncey |
| Group Leader responsible for the project: | Rob Halsall |
| Division Head responsible for the project: | Steve Quinton |
| Project Managers of related projects: | John Coughlan |
| Programme Manager: | Steve Quinton |
| Quality Manager: | Steve Quinton |

# Description

Design & production of a 96-channel ADC-FPGA instrumentation module in a 9U x 400mm VME64x form-factor for CALICE ECAL beam test in 2004.

In order to save time & development costs the design will re-use the Back End section of the CMS Tracker FED ADC-FPGA module and associated firmware.

The CMS FED Module is a monolithic 9Ux400mm VME Form Factor PCB constructed using modular design as 8 identical ADC-FPGA Front End (FE) Modules connected to an FPGA based Back End (BE) section.

The CMS ADC-FPGA FE modules will be replaced with a CALICE specific design but the CMS BE section will be retained with only minor modifications including firmware.

The new CALICE FE module will have 12 differential analogue and 27 LVDS electrical inputs via a dual front panel VHDCI SCSI connector. The ADC will be a dual 16 bit part with a sampling rate of 500 kHz and the FPGA will be a Virtex II part.

The CALICE FE modules will be required to have the same I/O, control and data communications protocols as the CMS FE modules.

A Jumper array in each FE module will allow some flexibility in selecting the amount of analogue versus digital I/O on the input connector, see table in section 2.3.

Buffer requirements in the BE section will be increased to 8 Mbytes in order to allow for complete buffering of data from a spill – this reduces the requirements on the VME interface data rate to 2 Mbyte/s.

Additionally the option exists to add the trigger logic to the BE Section BE FPGA which reduces the need for an extra module in the system.

## Scope

## Includes

System Design Consultancy

Design of the ADC/FPGA FE Module

Procurement and production of 2 prototypes

Basic Test of prototype ADC modules including JTAG

Procurement and production of 9 final modules

Procurement of cables - 10 prototypes and 64 production

Basic Test of final ADC modules including JTAG

Access to CMS VHDL FPGA firmware & limited support

## Excludes

Development of CALICE Front End firmware

Development of CALICE Trigger firmware

Integration and test of CALICE firmware

CALICE System Software

VME Crate and VME-PC link

# Deliverables

2 Prototype Boards

9 Production Boards

10 prototype Cables

64 production cables

Board Documentation

Access to CMS VHDL FPGA Firmware & documentation

## Constraints

## Budget

Total budget for RAL deliverables estimated at £95.4K hardware & 25 Staff Months effort.

## Schedule

Milestone Summary;

Global

| Prototype Design Complete | 24-10-2003 |
| --- | --- |
| Prototype Fabrication Complete | 17-11-2003 |
| Prototype Testing Complete | 31-03-2004 |
| Design Iteration Complete | 31-04-2004 |
| Production Board Fabrication Complete | 31-05-2004 |
| Production Board Testing Complete | 30-07-2004 |

PCB

| PCB tape out | Fri 24/10/03 |
| --- | --- |
| Assembled PCB at RAL | Fri 14/11/03 |
| Module ready for FPGA development | Tue 18/11/03 - earliest |

Basic Test Development

| Basic ADC performance tests firmware ready | Tue 18/11/03 |
| --- | --- |
| Basic ADC performance tests complete | Fri 12/12/03 |

VFE Test Development

| Ready for VFE tests | Fri 05/12/03 |
| --- | --- |
| VFE Test complete | Fri 12/12/03 |

Final System Test Development

| Final firmware development start | Thu 06/11/03 |
| --- | --- |
| FE-BE FPGA Integration Complete | Wed 03/12/03 |

## Performance

Front End Module;

| Parameter | Value | Note | Comment |
| --- | --- | --- | --- |
| No of Analogue Inputs | 12 (6) | 1 | Differential |
| Analogue input | +/- 1.25V | 2 | Into 120R nominal about 0V |
| ADC type | ADS8361 |  | Analogue Devices |
| No of Analogue outputs | 1 (1)* |  | Differential |
| Analogue outputs | +/- 1.25V into 120 R |  | ( +/- 2.5v Into open circuit) 120 R output impedance. |
| DAC type | ? |  |  |
| No of Digital input/outputs | 21 (27)* |  | Differential 120 R |
| Digital I/O | Bus LVDS |  | Virtex II –4 speed grade |

Back End Section;

| Parameter | Value | Note | Comment |
| --- | --- | --- | --- |
| Data Merging | 8 @ 80 Mbyte/s |  |  |
| Synchronous Controls | 8 x 8 @ 40 MHz |  |  |
| Data Buffer | 8 Mbytes |  |  |
| VME | 32A/32D with BLT |  |  |
| VME | 2 Mbytes/s |  | Average |

Notes;

1. Configurable via jumpers

2. Assumes Madison universal SCSII cable 120 R – non halogen free

## Regulatory

The module will not be EMC tested.

# IPR and Confidentiality

Schematics and layouts are marked CCLRC copyright

All CCLRC-RAL supplied schematics, layouts, source code should be treated as confidential, for non-commercial use and restricted for use on CALICE project.

# Project Monitoring

Customers will hold their own progress meetings.

Internal Project Monitoring will be by weekly Project Monitor Forms