## Project Monitor Form

| Project: Calice | PMF number: 0017 |  |  |
| --- | --- | --- | --- |
| Date: 14-November-2003 | Sheet: 1 | of | 3 |
| # News and comment |  |  |  |
| Dates; Next Calice Electronics Meeting is Thursday 20th November at RAL. Basic test (Chipscope & VIO) firmware preparation at RAL Tuesday 18th November. PCB manufacture status; Two PCBs arrived at RAL on Monday and were delivered to ID by late afternoon. They were visually inspected and checked for Power shorts and potential assembly problems by Adam on Tuesday morning. The assembly company collected them on Wednesday morning – This represents a 2-day slippage against the schedule. PCB Design Status; Drawings have been completed by the DO – sign off is outstanding. Assembly status; The assembly company picked up the two PCBs on Wednesday morning. Estimated delivery date of assembled modules to RAL is now Friday 21st November. Procurement status; We have now arranged to borrow the (8 Off) cables for the JTAG tests. Additionally, it should be noted that, we do not need a full set of eight cables to carry out the JTAG tests - we can do the test in stages moving the cable(s) between pairs of connectors. Manufacture of the NIM to LVDS module is in progress and delivery of the module to Calice is expected during the week of the 23rd November. The last components to arrive, the QDR memories should be at RAL tomorrow - this will be in time to make assembly on to the board. All other components are at the assembly company including the strengthening bars. The front panel has gone out for manufacture and delivery is expected by Friday 27th November. Test status; JTAG test preparation is mostly complete and is expected to be ready well in advance of the boards being available Paul Dauncey & Dan Bowerman delivered the Linux PC to RAL on Thursday 13-11-2003. The PC is set up and working at RAL in the R25 test lab. Initial tests with the SBS VME interface and a bus monitor card in the mini 9U VME crate show that the PC to VME interface is working. Further tests with the CMS FED board showed that we were able to access some of the registers. Additionally the RS232 operation was tested using a Virtex II development board with Rob Halsall’s RS232 firmware – this appeared to work as well as the equivalent Python code. #### Firmware status The earliest possible date for firmware (basic test package) to be required is now Friday the 21st November 2003 assuming JTAG tests proceed without problems. At RAL work is in progress to test the operation of the Chipscope and Virtual IO – early results show that we can successfully run a VIO and chipscope core in the FPGA on the development board. On Tuesday November 18th we will begin to integrate parts of the front-end fpga design with the chipscope & VIO controls as required for the basic tests post JTAG. QA documentation status; Version 0.1 of the Project Spec documentation has been updated and distributed as planned. Feedback has been received from Adam and Paul - any changes will be added and the version increased to 0.2. Project Spec approval is now expected to occur on 18-11-2003. |  |  |  |

| # Actions from the previous PMF |  |  |  |
| --- | --- | --- | --- |
| Action | Status | Who | Target date |
| Sign of Schematics, Assembly, drill, kiting list etc in DO | Documents generated, still awaiting sign off | SAB | 7-11-2003 |
| Get network addresses for ICs LINUX PC | Done | RH | 10-11-2003 |
| Progress 10 Off cable order | Done | SAB | 7-11-2003 |
| Check on web location of CMS VME documentation | Not available yet | RH | 10-11-2003 |
| Check to see if Calice VME64x Crate can be tested by ESSG | Done | RH | 10-11-2003 |
| Try out Chipscope VIO core generator on development board | Done | EF | 14-11-2003 |
| Discuss JTAG tests in detail with Richard Matson | In Progress | SAB | 14-11-2003 |

| # Actions outstanding and new actions |  |  |
| --- | --- | --- |
| Action | Who | Target Date |
| Sign off Schematics, Assembly, drill, kiting list etc in DO | ### SAB | 10-11-2003 |
| E-mail web location of CMS VME documentation to Paul Dauncey | RH | 21-11-2003 |
| Refine use of Chipscope & VIO cores on development board | ### EF | 18-11-2003 |
| Continue to discuss JTAG tests in detail with Richard Matson | SAB | 21-11-2003 |
| Test Calice Crate and install in Rack | ### IC | 18-11-2003 |
| Make VME/BE FPGA clock distribution source available | IC | 18-11-2003 |
| Arrange a meeting with Dave Mercer to discuss Final Firmware development | RH | 18-11-2003 |

Project Monitor Form- milestones

| Project: Calice |  | PMF number: 16 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager: Rob Halsall |  |  |  |  |  |  |
| Date: |  | Sheet: |  | of |  |  |
|  | Milestones from Project Management Plan Version: | date due in PMP | predicted date |  |  | date done |
| 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 | Project Spec Sign Off Prototype Design Complete Prototype Fabrication Complete Prototype Testing Complete Design Iteration Complete Production Board Fabrication Complete Production Board Testing Complete PCB tape out Assembled PCB at RAL Module ready for FPGA development (earliest) Basic ADC performance tests firmware ready Basic ADC performance tests complete Ready for VFE tests VFE Test complete Final firmware development start FE-BE FPGA Integration Complete | ------------- | 7-11-2003 24-10-2003 17-11-2003 31-03-2004 31-04-2004 31-05-2004 30-07-2004 24/10/03 14/11/03 18/11/03 18/11/03 12/12/03 05/12/03 12/12/03 06/11/03 03/12/03 |  |  |  |