## Project Monitor Form

| Project: Calice | PMF number: 0018 |  |  |
| --- | --- | --- | --- |
| Date: 21-November-2003 | Sheet: 1 | of | 3 |
| # News and comment |  |  |  |
| Dates; Calice Electronics Meeting was held at RAL on Thursday 20th November at RAL – see minutes on Calice UK Web site at http://www.hep.ph.ic.ac.uk/calice/elecMeetings/031120ral/minutes.txt. Next meeting is Thursday 27th November at RAL. Rob Halsall was on sick leave for 3 days up to the 21st November – this report is written retrospectively for completeness. PCB Design Status; Drawings have been completed by the DO – sign off is outstanding. Assembly status; Two assembled PCBs are expected at RAL today Procurement status; The QDR memories have not arrived in time and will not be fitted to the modules. Manufacture of the NIM to LVDS module is in progress and delivery of the module to Calice is expected during the week of the 23rd November. The front panel is expected by Friday 27th November. Test status; JTAG test preparation is mostly complete – some complications to compensate for the the missing QDRs. Earliest date for JTAG test completion is now Tuesday 25th November. #### Firmware status The earliest possible date for firmware (basic test package) to be required is now Tuesday the 25th November 2003 assuming JTAG tests proceed without problems. Work started on Tuesday November 18th to integrate parts of the front-end fpga design with the chipscope & VIO controls as required for the basic tests post JTAG. This work was not conclusive as some integration problems were encountered. QA documentation status; Version 0.1 of the Project Spec documentation has been updated and distributed as planned. Feedback has been received from Adam and Paul - any changes will be added and the version increased to 0.2. Project Spec approval is now expected to occur on 28-11-2003. |  |  |  |

| # Actions from the previous PMF |  |  |  |
| --- | --- | --- | --- |
| Action | Status | Who | Target date |
| Sign off Schematics, Assembly, drill, kiting list etc in DO | Documents generated, still awaiting sign off | SAB | 28-11-2003 |
| Check on web location of CMS VME documentation | Not available yet | RH | 28-11-2003 |
| Make VME/BE FPGA clock distribution source available | Done | IC | 18-11-2003 |
| Install & Test VME Crate | Done | IC | 18-11-03 |
| Discuss JTAG tests with Richard Matson | In Progress | SAB | 14-11-2003 |

| # Actions outstanding and new actions |  |  |
| --- | --- | --- |
| Action | Who | Target Date |
| Sign off Schematics, Assembly, drill, kiting list etc in DO | ### SAB | 10-11-2003 |
| E-mail web location of CMS VME documentation to Paul Dauncey | RH | 28-11-2003 |
| Work on Integration of Chipscope & VIO cores with FE FPGA code | ### EF | 28-11-2003 |
| Continue to discuss JTAG tests with Richard Matson | SAB | 21-11-2003 |
| Arrange a meeting with Dave Mercer to discuss Final Firmware development | RH | 28-11-2003 |

Project Monitor Form- milestones

| Project: Calice |  | PMF number: 16 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager: Rob Halsall |  |  |  |  |  |  |
| Date: |  | Sheet: |  | of |  |  |
|  | Milestones from Project Management Plan Version: | date due in PMP | predicted date |  |  | date done |
| 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 | Project Spec Sign Off Prototype Design Complete Prototype Fabrication Complete Prototype Testing Complete Design Iteration Complete Production Board Fabrication Complete Production Board Testing Complete PCB tape out Assembled PCB at RAL Module ready for FPGA development (earliest) Basic ADC performance tests firmware ready Basic ADC performance tests complete Ready for VFE tests VFE Test complete Final firmware development start FE-BE FPGA Integration Complete | ------------- | 7-11-2003 24-10-2003 17-11-2003 31-03-2004 31-04-2004 31-05-2004 30-07-2004 24/10/03 14/11/03 18/11/03 18/11/03 12/12/03 05/12/03 12/12/03 06/11/03 03/12/03 |  |  |  |