## Project Monitor Form

| Project: Calice | PMF number: 0019 |  |  |
| --- | --- | --- | --- |
| Date: 28-November-2003 | Sheet: 1 | of | 3 |
| # News and comment |  |  |  |
| Dates; The Calice Electronics Meeting was held at RAL on Thursday 27th November at RAL – see minutes on Calice UK Web site at http://www.hep.ph.ic.ac.uk/calice/elecMeetings/031127ral/minutes.txt when available. Next meeting is Tuesday 9th November, 2pm, at RAL. It is now likely that the VFE modules will not be ready for December testing and also there is the possibility that the tests can be done at RAL – this needs to be investigated. PCB Design Status; Drawings have been completed by the DO – status of sign off is not known. Assembly status; Two assembled PCBs arrived as expected on Friday the 21st November. Procurement status; The QDR memories are now not due to arrive until the end of December – an alternatives are under investigation which are ex stock but we need to confirm that it can do the job technically. Manufacture of the NIM to LVDS module is almost complete but delivery of the module to Calice is now expected during the first week of the December. This is not on the critical path yet. We do not have the ‘parallel’ jumpers yet so both boards have had to be fitted with individual jumpers – the correct jumpers are expected to be available for production. The front panel is ready and delivery is expected on Monday the 1st of December. Test status; The first module to bet tested S/No 02 passed JTAG tests on Tuesday 25th November. The second module to be tested S/No 01 passed JTAG tests on the 27th November. Some problems were encountered with the Power Supply sequencing – on power up from cold the modules need to have reset button pressed to get the power to come up correctly. James Salisbury will look into this problem. One or two solder joint problems have been found (non BGA in PSU section) and one or two capacitors have been assembled instead of resistors (detected by JTAG testing). #### Firmware status The modules are basically available for firmware testing from Tuesday the 27th November 2003 - initial testing began after the electronics meeting. QA documentation status; Version 0.1 of the Project Spec documentation has been updated and distributed as planned. Feedback has been received from Adam and Paul - any changes will be added and the version increased to 0.2. Project Spec approval is now expected to occur on 3-12-2003. |  |  |  |

| # Actions from the previous PMF |  |  |  |
| --- | --- | --- | --- |
| Action | Status | Who | Target date |
| Sign off Schematics, Assembly, drill, kiting list etc in DO | Documents generated, status unknown | SAB | 1-12-2003 |
| Check on web location of CMS VME documentation | Not available yet | RH | 5-12-2003 |
| Work on Integration of Chipscope & VIO cores with FE FPGA code | ### Ongoing | EF | 5-12-2003 |
| Discuss JTAG tests with Richard Matson | Done | SAB | 14-11-2003 |

| # Actions outstanding and new actions |  |  |
| --- | --- | --- |
| Action | Who | Target Date |
| Sign off Schematics, Assembly, drill, kiting list etc in DO | ### SAB | 1-12-2003 |
| E-mail web location of CMS VME documentation to Paul Dauncey | RH | 5-12-2003 |
| Work on Integration of Chipscope & VIO cores with FE FPGA code | ### EF | 5-12-2003 |
| Arrange a meeting with Dave Mercer to discuss Final Firmware development | RH | 5-12-2003 |
| Provide support & consultancy for testing as required | IC/SAB | 5-12-2003 |
| Investigate & provide support for power sequencing issues | JS | 5-12-2003 |
| Provide consultancy for BE/VME FPGA | ST/EF | 5-12-2003 |
| Update Project Spec and sign off | RH | 3-12-2003 |

Project Monitor Form- milestones

| Project: Calice |  | PMF number: 16 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager: Rob Halsall |  |  |  |  |  |  |
| Date: |  | Sheet: 3 |  | of | 3 |  |
|  | Milestones from Project Management Plan Version: | date due in PMP | predicted date |  |  | date done |
| 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 | Project Spec Sign Off Prototype Design Complete Prototype Fabrication Complete Prototype Testing Complete Design Iteration Complete Production Board Fabrication Complete Production Board Testing Complete PCB tape out Assembled PCB at RAL Module ready for FPGA development (earliest) Basic ADC performance tests firmware ready Basic ADC performance tests complete Ready for VFE tests VFE Test complete Final firmware development start FE-BE FPGA Integration Complete | ------------- | 7-11-2003 24-10-2003 17-11-2003 31-03-2004 31-04-2004 31-05-2004 30-07-2004 24/10/03 14/11/03 18/11/03 18/11/03 12/12/03 05/12/03 12/12/03 06/11/03 03/12/03 |  |  | 23-10-2003 21-11-2003 27-11-2003 |