## Project Monitor Form

| Project: Calice | PMF number: 0020 |  |  |
| --- | --- | --- | --- |
| Date: 05-December-2003 | Sheet: 1 | of | 3 |
| # News and comment |  |  |  |
| Dates; The minutes of the Calice Electronics Meeting held on Thursday 27th November at RAL are now available on the Calice UK Web site at http://www.hep.ph.ic.ac.uk/calice/elecMeetings/031127ral/minutes.txt. The next meeting is Tuesday 9th December, 2pm, at RAL – this was incorrectly reported in the previous PMF as November. PCB Design Status; Drawings have been signed off Procurement status; The QDR memories are due to arrive at the end of December – this is not on the critical path as we can work around the problem but the date needs to be double checked to make sure it is not any later. The alternative QDR part available ex stock is ‘burst of 4’ which would probably require too much re-design of the firmware. As long as the delivery is ok our best option is to wait for correct parts to be delivered. The NIM to LVDS module was delivered on the 4th December. We now have samples of the parallel jumpers – 500 Off (MOQ) have been ordered. The front panels have been delivered and fitted. Adam has tested the cables for mechanical fit in all positions with no problems. Other comments; LED’s are a tight fit, Hot swap switch needs to be fitted & labelling is 1 to 8 when it should have been 0 to 7. SCSI connectors have been sent to Paris. Test & Firmware status; Work has been proceeding on three fronts Software development with the CMS Tracker FED using the existing FED firmware, RS232 readout on the CERC and chipscope/VIO development with the FE FPGA firmware on the CERC looking at the ADC & DAC. RS232 readout has been successfully tested in the CERC – Memory tests were carried out on Block RAMs in the FE FPGAs. This actually requires firmware running in the BE & VME FPGA as well as the FE FPGAs. The RS232 signals were converted to LVDS using a development board and fed into the BE FPGA via the backplane. The latest version was issued today. Work on the FE FPGA code with chipscope is in progress – The DAC has been scanned through it’s range in powers of 2 using chipscope/VIO but the readout of the ADC is still ongoing. Current status is that the ADC appears to convert but the data appears to be zero. Some manual probing of a sample of the analogue circuitry has been performed – voltage references appear to be correct. This work continues. The software development has used the CMS FED with FED FE, BE & VME Firmware. A meeting with the key CMS staff might be useful at some point to clarify the operation of the firmware and versions. Additionally the Block RAMs & some registers in the CERC VME interface have successfully accessed. System ACE is working on both cards. Some further dry joints have been found and fixed. James Salisbury has found & fixed one problem (missing connection) with the power circuitry related to the reset problem. The boards now power up correctly in the VME crate. We have not met the ‘ready for VFE tests’ milestone today but this is still a possibility for next week – the VFE module availability and plans for test needs to be investigated. Testing will continue next week at RAL. QA documentation status; Distribution of version 0.2. Project Spec is still outstanding. |  |  |  |

| # Actions from the previous PMF |  |  |  |
| --- | --- | --- | --- |
| Action | Status | Who | Target date |
| Sign off Schematics, Assembly, drill, kiting list etc in DO | Done | SAB | 1-12-2003 |
| Check on web location of CMS VME documentation | Not available yet | RH | 5-12-2003 |
| Work on Integration of Chipscope & VIO cores with FE FPGA code | ### Ongoing | EF | 5-12-2003 |
| Provide support & consultancy for testing as required | Ongoing | IC/SAB | 5-12-2003 |
| Provide consultancy for BE/VME FPGA | Ongoing | ST/EF | 5-12-2003 |
| Update Project Spec and sign off | Ongoing | RH | 5-12-2003 |

| # Actions outstanding and new actions |  |  |
| --- | --- | --- |
| Action | Who | Target Date |
| E-mail web location of CMS VME documentation to Paul Dauncey | RH | 12-12-2003 |
| Work on Integration of Chipscope & VIO cores with FE FPGA code | ### EF | 12-12-2003 |
| Arrange a meeting with Dave Mercer to discuss Final Firmware development | RH | 12-12-2003 |
| Provide support & consultancy for testing as required | IC/SAB | 12-12-2003 |
| Investigate & provide support for power sequencing issues | JS | 12-12-2003 |
| Provide consultancy for BE/VME FPGA | ST/EF | 12-12-2003 |
| Confirm QDR Delivery | SAB | 12-12-2003 |
| Make sure Route Cards & Problem Reports up to date | SAB | 12-12-2003 |
| Order 128MB Compact Flash cards, 11 Off | RH | 12-12-2003 |
| Investigate VFE availability & Test Plans | SAB/PD | 12-12-2003 |
| Update Project Spec and sign off | RH | 12-12-2003 |

Project Monitor Form- milestones

| Project: Calice |  | PMF number: 20 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager: Rob Halsall |  |  |  |  |  |  |
| Date: 05-December-2003 |  | Sheet: 3 |  | of | 3 |  |
|  | Milestones from Project Management Plan Version: | date due in PMP | predicted date |  |  | date done |
| 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 | Project Spec Sign Off Prototype Design Complete Prototype Fabrication Complete Prototype Testing Complete Design Iteration Complete Production Board Fabrication Complete Production Board Testing Complete PCB tape out Assembled PCB at RAL Module ready for FPGA development (earliest) Basic ADC performance tests firmware ready Basic ADC performance tests complete Ready for VFE tests VFE Test complete Final firmware development start FE-BE FPGA Integration Complete | ------------- | 7-11-2003 24-10-2003 17-11-2003 31-03-2004 31-04-2004 31-05-2004 30-07-2004 24/10/03 14/11/03 18/11/03 18/11/03 12/12/03 05/12/03 12/12/03 06/11/03 03/12/03 |  |  | 23-10-2003 21-11-2003 27-11-2003 |