## Sheet1
PARTICLE PHYSICS PROJECTS RISK PROFORMA
Ref | Risk Description | Potential impact on project | Inherent Risk Score |  |  | Existing Controls | Mitigating factors | Residual risk score |  |  | Comment | Proposed Action
|  |  | L | I | L×I |  |  | L | I | L×I
WP1.1 | Failure of ECAL wafer fabrication | Loss of some ECAL layers leading to less useful data | 2 | 2 | 4 | Non-UK: Sourcing wafers from four manufacturers | Perform studies of layer arrangement to minimise impact of missing layers | 2 | 2 | 4
WP1.2a | Failure of AHCAL system | Loss of data for simulation comparisions | 2 | 2 | 4 | Non-UK: Technical Board reviews every six months | System already running and test beam data taken | 1 | 2 | 2
WP1.2b | Failure of DHCAL systems | Loss of data for simulation comparisions | 3 | 1 | 3 | Non-UK: Technical Board reviews every six months
WP1.3 | Extended beam test period required due to problems with calorimeters, beams or DAQ | Higher travel costs | 2 | 1 | 2 | Thorough testing of equipment before shipping. Visit beam areas and understand environment before beam test | We have budgetted for around £1k/week for the beam test | 2 | 1 | 2
WP2.1 | Failure of VFE ASIC production so no chips available for PCB test | Non-verification of ASIC by time of TDR | 1 | 2 | 2 | Non-UK: Review ASIC design before each fabrication round |  | 1 | 2 | 2
WP2.2 | Not able to find manufacturer for 1.5m PCBs | Study not completed in time for TDR | 2 | 2 | 4 | Investigate several PCB manufacturers | Rely on smaller PCB stitching techniques, which may become the baseline in any case | 2 | 2 | 4
WP2.3 | Delays in sourcing off-detector receiver components | Delays in tests | 1 | 2 | 2 | Consider alternative components and/or suppliers | Continue work with partially completed engineering version of boards | 1 | 2 | 2
WP3.1 | Failure of sensor fabrication round | Three to four month delay in schedule and extra cost to remake | 2 | 2 | 4 | Regular design reviews according to ISO9000 specifications | Prepare tests before fabrication complete so major errors can be identified immediately | 2 | 2 | 4
WP4.1 | Failure to develop suitable techniques for large-scale assembly | UK does not construct detector |  | 5 |  |  | Feed back to electronics/mechanical designers to modify slab design to simplify assembly |  |  |  | 2006-11-01
WP5.1 | No significant use of UK algorithms outside UK | Loss of influence/leadership in medium term | 2 | 2 | 4 | Ensure algorithms widely used by UK groups, increases exposure | UK groups work well together and collaborate with groups around world | 2 | 2 | 4
WP5.2 | UK studies make no significant impact on overall detector design | Loss of influence/leadership in medium term | 2 | 2 | 4 | Ensure studies performed are written up and included in detector concept reports | Process already started, e.g. for LDC | 2 | 2 | 4
All.1 | Delays/problems with RA appointments | Less impact on projects | 2 | 1 | 2 | Schedule recruitment period well in advance | Three of the five new project RAs are now in post | 2 | 1 | 2
All.2 | Loss of staff with required skills | Loss of expertise mid-way, causing delays | 3 | 2 | 6 | Ensure personnel work closely with other UK colleagues so no one individual alone has critical knowledge |  | 3 | 2 | 6
All.3 | Illness of staff in critical positions | Reallocation of effort causing delays | 2 | 2 | 4 | As above |  | 2 | 2 | 4
L = Likelihood on scale of 1, 2 ,3 4 where 1 is low.
I = Impact on scale of 1, 2, 3, 5 where 1 is low.
High risk is a score greater than 8
2006-11-15