Milestone Tables

| Table 1. Milestones for the period Sep 2006 – May 2007 |  |  |
| --- | --- | --- |
| WP1.19 Successful end of 2006 CERN test beam run | Oct 2006 | Achieved |
| WP1.27 Present interim results at LCWS07 | May 2007 | Achieved |
| WP2.67 Present simulation results | Dec 2006 | Complete Apr 2007 |
| WP2.17 Test bench 0 hardware ready and commissioned | Jan 2007 | Complete May 2007 |
| WP2.40 Report on FPGA Ethernet work | Jan 2007 | Complete Apr 2007 |
| WP2.56 Acquire optical switch | Mar 2007 | Complete May 2007 |
| WP2.90 Initial prototype complete | Mar 2007 | Achieved |
| WP3.5 First sensor interim design review | Oct 2006 | Complete Jan 2007 |
| WP3.6 First sensor design review | Dec 2006 | Complete Mar 2007 |
| WP3.7 First sensor design to foundry | Jan 2007 | Complete Apr 2007 |
| WP3.9 First sensor fabrication complete | May 2007 | Expected Jul 2007 |
| WP4.4 Glue literature research report | Sep 2006 | Complete Dec 2006 |
| WP4.7 Report on glue ageing results | May 2007 | Achieved |
| WP5.34 Generic physics analysis implemented | Sep 2006 | Achieved |
| WP5.16 Present first physics benchmarks results at Valencia | Nov 2006 | Milestone deleted (see note 2 at end) |
| WP5.11 Presentation of physics benchmark results at LCWS07 | Apr 2007 | Achieved |

| Table 2. Milestones for the period Jun – Dec 2007 |  |
| --- | --- |
| WP1.14 Complete analysis of DESY data | Expected Oct 2007 |
| WP1.20 Successful end of 2007 CERN test beam run | Expected Aug 2007 |
| WP1.24 Submit paper on electron results | Expected Dec 2007 |
| WP1.29 Complete internal report on hadron data | Dec 2007 |
| WP2.70 Make proposal for robust/flexible system | Jun 2007 |
| WP2.73 Demonstrate remote FPGA reset and reconfigure | Jun 2007 |
| WP2.20 Concepts established for 1.5m data path | Jul 2007 |
| WP2.7 Successful readout of 2007 ASICs | Retired |
| WP2.50 Component selection | Sep 2007 |
| WP2.77 Demonstrate system lock and data interface | Sep 2007 |
| WP2.94 Initial system complete | Dec 2007 |
| WP3.14 Second sensor interim design review | Expected Dec 2007 |
| WP3.15 Second sensor design review | Expected Mar 2008 |
| WP5.36 Alternative benchmark analysis available | Sep 2007 |
| WP5.24 First results from mechanical imperfections simulation | Dec 2007 |

| Table 3 – Overall milestone list |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | As at Sep 2006 | As at May 2007 Changes in bold | Delay due to |  | Affects critical path? | See note |
|  |  |  | UK? | Other Collabor-ators? |  |  |
| WP1.9 Successful end of DESY test beam run | May 2005 | Achieved |  |  |  |  |
| WP1.19 Successful end of 2006 CERN test beam run | Oct 2006 | Achieved |  |  |  |  |
| WP1.27 Present interim results at LCWS07 | May 2007 | Achieved |  |  |  |  |
| WP1.14 Complete analysis of DESY data | Jun 2007 | Expected Oct 2007 |  |  |  |  |
| WP1.20 Successful end of 2007 CERN test beam run | Jul 2007 | Expected Aug 2007 | N |  | N |  |
| WP1.24 Submit paper on electron results | Sep 2007 | Expected Dec 2007 |  |  |  |  |
| WP1.29 Complete internal report on hadron data | Dec 2007 | Dec 2007 |  |  |  |  |
| WP1.33 Successful completion of FNAL test beam run | Jun 2008 | Expected Sep 2008 |  |  |  |  |
| WP1.37 Submit paper on hadron results | Mar 2009 | Mar 2009 |  |  |  |  |
| WP2.86 Buy PCI cards | May 2006 | Achieved |  |  |  |  |
| WP2.66 Present simulation results | Dec 2006 | Complete Apr 2007 |  |  |  |  |
| WP2.17 Test bench 0 hardware ready and commissioned | Jan 2007 | Complete May 2007 |  |  |  |  |
| WP2.40 Report on FPGA Ethernet work | Jan 2007 | Complete Apr 2007 |  |  |  |  |
| WP2.56 Acquire optical switch | Mar 2007 | Complete May 2007 | Y | N | N |  |
| WP2.90 Initial prototype complete | Mar 2007 | Achieved |  |  |  |  |
| WP2.70 Make proposal for robust/flexible system | Jun 2007 | Jun 2007 |  |  |  |  |
| WP2.73 Demonstrate remote FPGA reset and reconfigure | Jun 2007 | Jun 2007 |  |  |  |  |
| WP2.20 Concepts established for 1.5m data path | Jul 2007 | Jul 2007 |  |  |  |  |
| WP2.7 Successful readout of 2007 ASICs | Sep 2007 | Retired | N | Y | N | 4 |
| WP2.50 Component selection | Sep 2007 | Sep 2007 |  |  |  |  |
| WP2.77 Demonstrate system lock and data interface | Sep 2007 | Sep 2007 |  |  |  |  |
| WP2.94 Initial system complete | Dec 2007 | Dec 2007 |  |  |  |  |
| WP2.23 Test bench 1 hardware ready and commissioned | Jan 2008 | Jan 2008 |  |  |  |  |
| WP2.60 Demonstrate optically switched network | Jan 2008 | Jan 2008 |  |  |  |  |
| WP2.43 Report on suitability of FPGAs for real-time conversion | Feb 2008 | Feb 2008 |  |  |  |  |
| WP2.80 Demonstrate trigger can C + C interface | Jun 2008 | Jun 2008 |  |  |  |  |
| WP2.27 Realistic design of VFE system established | Aug 2008 | Aug 2008 |  |  |  |  |
| WP2.53 Report on 10Gb performance | Aug 2008 | Aug 2008 |  |  |  |  |
| WP2.12 Successful readout of 2008 ASICs | Sep 2008 | Sep 2008 |  |  |  |  |
| WP2.30 VFE design finished | Oct 2008 | Oct 2008 |  |  |  |  |
| WP2.32 Freeze VFE system design | Dec 2008 | Dec 2008 |  |  |  |  |
| WP2.34 Complete draft of TDR section | Feb 2009 | Feb 2009 |  |  |  |  |
| WP2.64 Delivery of busy system | Mar 2009 | Mar 2009 |  |  |  |  |
| WP2.83 Demonstrate work-ability from single trigger | Mar 2009 | Mar 2009 |  |  |  |  |
| WP3.3 Preliminary design review | Apr 2006 | Achieved |  |  |  |  |
| WP3.5 First sensor interim design review | Oct 2006 | Complete Jan 2007 |  |  |  |  |
| WP3.6 First sensor design review | Dec 2006 | Complete Mar 2007 | Y | N | Y | 1 |
| WP3.7 First sensor design to foundry | Jan 2007 | Complete Apr 2007 | Y | N | Y | 1 |
| WP3.9 First sensor fabrication complete | May 2007 | Expected Jul 2007 | Y | N | Y | 1 |
| WP3.14 Second sensor interim design review | Sep 2007 | Expected Dec 2007 | Y | N | Y | 1 |
| WP3.15 Second sensor design review | Dec 2007 | Expected Mar 2008 | Y | N | Y | 1 |
| WP3.16 Second sensor design to foundry | Jan 2008 | Expected Apr 2008 | Y | N | Y | 1 |
| WP3.18 Second fabrication complete | May 2008 | Expected Aug 2008 | Y | N | Y | 1 |
| WP3.24 Beam tests start | Oct 2008 | Expected Dec 2008 | Y | N | Y | 1 |
| WP4.13 Thermal simulation report | Jan 2006 | Achieved |  |  |  |  |
| WP4.4 Glue literature research report | Sep 2006 | Complete Jan 2007 | Y | N | N |  |
| WP4.7 Report on glue ageing results | May 2007 | Achieved |  |  |  |  |
| WP4.17 Cooling system proposal | Apr 2008 | Apr 2008 |  |  |  |  |
| WP4.25 Assembly design report | Mar 2009 | Mar 2009 |  |  |  |  |
| WP5.14 Present initial result from single particle studies | Mar 2006 | Achieved |  |  |  |  |
| WP5.26 MAPS implemented in Mokka | May 2006 | Achieved |  |  |  |  |
| WP5.33 Status report at regional workshop | May 2006 | Achieved |  |  |  |  |
| WP5.4 Comparison of existing PFAs | Jun 2006 | Achieved |  |  |  |  |
| WP5.8 Release of V1 of algorithm | Aug 2006 | Achieved |  |  |  |  |
| WP5.34 Generic physics analysis implemented | Sep 2006 | Achieved |  |  |  |  |
| WP5.16 Present first physics benchmarks results at Valencia | Nov 2006 | Deleted | Y | N | N | 2 |
| WP5.11 Presentation of physics benchmark results at LCWS07 | Apr 2007 | May 2007 | N |  | N | 3 |
| WP5.36 Alternative benchmark analysis available | Sep 2007 | Sep 2007 |  |  |  |  |
| WP5.24 First results from mechanical imperfections simulation | Dec 2007 | Dec 2007 |  |  |  |  |
| WP5.28 Simulation of MAPS tets beam | Mar 2008 | Mar 2008 |  |  |  |  |
| WP5.38 Report on hadronic modelling studies with test beam | Jun 2008 | Jun 2008 |  |  |  |  |

Notes:

1. Simulation studies showed that additional design work of a deep p-well process by the foundry was required to achieve the target signal:noise ratio.

2. Initial results were presented earlier to collaboration meetings and we decided to wait until LCWS07 before presenting further results.

3. LCWS07 date fixed as May 2007 after we had set this benchmark.

4. Phase 1 of ASIC development skipped by our collaborators.