| CCLRC | RUTHERFORD APPLETON LABORATORY Internal Memorandum |
| --- | --- |

| To: Cc: | Budget Holders Caroline Gore | From: Date: | Joanne Metcalf Senior Management Accountant 19 September 2007 | Tel: Email | 01235 446398 J.M.Metcalf@rl.ac.uk |
| --- | --- | --- | --- | --- | --- |

PARTICLE PHYSICS SLA: OUTTURN FORECAST 2007-08

I am writing to ask you as a Budget Holder to analyse and report on the spend to date for your project(s) funded through the Particle Physics SLA programme, and to provide a first forecast of the total projected spend to the end of the year – the outturn forecast.  STFC is again under great pressure from Government this year to ensure that programmes achieve or spend very close to the outturn forecast so it is crucial that you are realistic in your projections.

This year, I am asking for your forecast a month earlier due to STFC financial reporting pressures. To assist you with this task, expenditure data up to the end of August 2007 is now available from FRS and your project’s budget allocations are listed on the form below. A report from the travel database has also been provided to help you analyse travel commitments.  It is also important to review STFC technology department (TD) staff effort bookings as part of the exercise to ascertain whether there are any potential issues (eg incorrect or over-/under booking of staff effort).  This data is available from the monthly reports provided by Caroline Gore, in our STBU Finance team. Please include a note of any booking errors or problems identified with effort usage in your return so we can action any corrections.

A proforma has been included below to help with the financial analysis and reporting.  Please identify and report separately on spend against each of your project’s budget allocations for TD effort, M&O, Requisitions and Travel where these have been allocated.  Please also highlight any major projected underspend/ overspend, the reasons for it and what actions are needed or being taken to correct it.

Budget holders should complete one proforma for each of their projects and return to Caroline Gore, STBU (email:C.Gore@rl.ac.uk) , no later than Friday 5 October 2007.  If Budget Holders wish to seek additional funds at this stage, a brief supporting case must also be submitted.

Once received, your returns will be incorporated in the Particle Physics SLA programme outturn forecast and the overall position reviewed with the Science Programmes Office.  Any significant changes to planned spend (either increases or decreases) will be considered, and the appropriate corrective action agreed and notified to you.

I look forward to receiving your outturn forecast(s) in due course.  In the meantime, should any of the above cause you difficulty, please let me know as soon as possible.

OUTTURN FORECAST 2007-08

| Project Name | CALICE |
| --- | --- |
| Project Code | FD317** |
| Budget Holder | Prof M Green Cc: Dr P Dauncey Prof M Tyndel |
| e-Mail address | M.Green@rhul.ac.uk P.Dauncey@imperial.ac.uk M.Tyndel@rl.ac.uk |

|  | Allocation £k | Spend to date £k | Outturn forecast £k |
| --- | --- | --- | --- |
| TD | 90.0 | 35.4 | 90.0 |
| Requisitions and M&O | 193.7+30.3=224.0 | 67.8 | 150.0 |
| Travel | 77.9 | 46.6* | 77.9 |
| Total | 391.9 | 149.8 | 317.9 |

Commentary/Explanation: * Includes commitments in the attached spreadsheet. Note that Requisitions and M&O are not separately coded in FRS and therefore are not separate but rather summed in the Requisitions and M&O line. The outturn forecast is lower than allocation as follows: - The allocation was higher than the original expected by around £15k due to funds shifting from 2006/7. - The WP3 Requisition line is lower by £40k because the foundry charges for the MAPS wafer productions are being charged at £34k in 2007/8 and £114k in 2008/9 rather than £74k in each FY as we had assumed. - The WP2 Requisition line is lower by £20k because significant items can now be purchased off the shelf rather than developed internally as originally planned.