## Total
Total | Approved | Transfers | Actual spend in previous years |  |  | Allocation to completion | Actual spend 2008/9 to end July | Total |  | Variance
| (excluding contingency) |  | (2) |  |  | (4) | (3) | Actual spend (2+3) | Projected spend (2+4) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | 2007/8 | 2008/9 |  | (6) | (7)
Birmingham Effort | 162.29 | 0 | 6.3 | 43.7715 | 59.6112 | 31.8 | 5 | 114.6827 | 141.4827 | -47.6073 | -20.8073
Cambridge Effort | 250.52 | 0 | 47.731 | 76.165 | 90.0519 | 68.1 | 33.8 | 247.7479 | 282.0479 | -2.7721 | 31.5279
ICL Effort | 282.57 | 0 | 22.512 | 56.2126 | 108.937 | 43.1 | 26.2 | 213.8616 | 230.7616 | -68.7084 | -51.8084
Manchester Effort | 216.51 | 0 | 29.75 | 41.4391 | 72.1987 | 34.8 | 11.6 | 154.9878 | 178.1878 | -61.5222 | -38.3222
RHUL Effort | 237.64 | 57.7 | 15.25 | 37.704 | 103.488 | 113.5 | 44.4 | 200.842 | 269.942 | -94.498 | -25.398
UCL Effort | 318.84 | -57.7 | 26.09 | 49.8132 | 116.1389 | 53.6 | 18 | 210.0421 | 245.6421 | -51.0979 | -15.4979
University Sub-Total1 | 1468.37 |  | 147.633 | 305.1054 | 550.4257 | 344.9 | 139 | 1142.1641 | 1348.0641 | -326.2059 | -120.3059
RAL PPD Effort | 289 | 0 | 11.54 | 53.61 | 103.5302 | 78.3 | 24.5 | 193.1802 | 246.9802 | -95.8198 | -42.0198
RAL ED/ID Effort | 277.2 | 0 | 14.38 | 82.32 | 89.9501 | 73.4 | 28.801 | 215.4511 | 260.0501 | -61.7489 | -17.1499
Equipment1 | 344.2 | 15 | 0 | 23.221 | 130.11 | 65 | 68.594 | 221.925 | 218.331 | -137.275 | -140.869
Travel | 221.9 | 0 | 24.123 | 49.852 | 77.85 | 49.0153 | 8.5 | 160.325 | 200.8403 | -61.575 | -21.0597
Consumables 1 | 103.5 | 0 | 1.635 | 17.8 | 20.06 | 20 | 5.334 | 44.829 | 59.495 | -58.671 | -44.005
Exceptional1
Total (excluding VAT and WA) | 2704.17 |  | 199.311 | 531.9084 | 971.926 | 630.6153 | 274.729 | 1977.8744 | 2317.7606 | -746.2956 | -401.4094
Working allowance | 166.1 | -15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -151.1
VAT
Total (including VAT & WA) | 2870.27 |  | 199.311 | 531.9084 | 971.926 | 630.6153 | 274.729 | 1972.8744 | 2317.7606 | -746.2956 | -552.5094
Contingency (held by STFC) | 152
Total Award | 3022.27
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## WP1
WP1 | Approved | Transfers | Actual spend in previous years |  |  | Allocation to completion | Actual spend 2008/9 to end July | Total |  | Variance
| (excluding contingency) |  | (2) |  |  | (4) | (3) | Actual spend (2+3) | Projected spend (2+4) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | 2007/8 | 2008/9 |  | (6) | (7)
Birmingham Effort | 9.79 |  | 3.15 | 3.6476 | 0 | 7.7 | 2.5 | 9.2976 | 14.4976 | -0.49237 | 4.7076
Cambridge Effort | 65.35 |  | 29.546 | 23.11 | 0 | 28.8 | 20.7 | 73.356 | 81.456 | 8.006 | 16.106
ICL Effort | 51.94 |  | 22.512 | 18.182 | 8.448 | 7.6 | 2.5 | 51.642 | 56.742 | -0.298 | 4.802
Manchester Effort | [7 empty] | 0
RHUL Effort | 9.94 |  | 4.7 | 5 | 0 | 58.7 | 22.2 | 31.9 | 68.4 | 21.96 | 58.46
UCL Effort | 38.63 |  | 6.61 | 4.7881 | 0 | 3 | 1 | 12.3981 | 14.3981 | -26.2319 | -24.2319
University Sub-Total1 | 175.65 |  | 66.518 | 54.7278 | 8.448 | 105.8 | 48.9 | 178.5938 | 235.4938 | 2.9438 | 59.8438
RAL PPD Effort
RAL ED/ID Effort
Equipment1
Travel | 111.7 |  | 16.7384 | 34.0718 | 32.2 | 20 | 4 | 87.0102 | 103.0102 | -24.6898 | -8.6898
Consumables 1 | 11.1 |  | 0.407 | 3.875 | 0 | 0 | 0.205 | 4.487 | 4.282 | -6.613 | -6.818
Exceptional1
Total (excluding VAT and WA) | 298.45 |  | 83.6634 | 92.6746 | 40.648 | 125.8 | 53.105 | 270.091 | 342.786 | -28.359 | 44.336
Working allowance | [7 empty] | 0 | 0 | 0 | 0
VAT
Total (including VAT & WA) | 298.45 |  | 83.6634 | 92.6746 | 40.648 | 125.8 | 53.105 | 270.091 | 342.786 | -28.359 | 44.336
Contingency (held by STFC)
Total Award | 298.45
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## WP2
WP2 | Approved | Transfers | Actual spend in previous years |  |  | Allocation to completion | Actual spend 2008/9 to end July | Total |  | Variance
| (excluding contingency) |  | (2) |  |  | (4) | (3) | Actual spend (2+3) | Projected spend (2+4) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | 2007/8 | 2008/9 |  | (6) | (7)
Birmingham Effort
Cambridge Effort | 113.31 |  | 18.185 | 29.945 | 41.1 | 25.4 | 8.5 | 97.73 | 114.63 | -15.58 | 1.32
ICL Effort | 90.43 |  | 0 | 16.2126 | 42.7574 | 0 |  | 58.97 | 58.97 | -31.46 | -31.46
Manchester Effort | 64.41 |  | 9.44 | 17.1901 | 19.7894 | 18.3 | 6.1 | 52.5195 | 64.7195 | -11.8905 | 0.30952
RHUL Effort | 103.9 | 57.7 | 5.85 | 22.867 | 48.3014 | 43.8 | 17.4 | 94.4184 | 120.8184 | -67.1816 | -40.7816
UCL Effort | 243.31 | -57.7 | 19.48 | 45.0251 | 95.9165 | 50.6 | 17 | 177.4215 | 211.0215 | -8.1885 | 25.4115
University Sub-Total1 | 615.36 |  | 52.955 | 131.2397 | 247.8648 | 138.1 | 49 | 481.0595 | 570.1595 | -134.3005 | -45.2005
RAL PPD Effort
RAL ED/ID Effort
Equipment1 | 118.1 |  | 0 | 8.114 | 65 | 25 | 8.594 | 81.708 | 98.114 | -36.392 | -19.986
Travel | 24.9 |  | 2.9538 | 3.7885 | 9.5 | 10 | 2 | 18.2423 | 26.2423 | -6.6577 | 1.3423
Consumables 1 | 19.6 |  | 0 | 13.908 | 6.34 | 0 |  | 20.248 | 20.248 | 0.648 | 0.648
Exceptional1
Total (excluding VAT and WA) | 777.96 |  | 55.9088 | 157.0502 | 328.7048 | 173.1 | 59.594 | 601.2578 | 714.7638 | -176.7022 | -63.1962
Working allowance | [7 empty] | 0 | 0 | 0 | 0
VAT
Total (including VAT & WA) | 777.96 |  | 55.9088 | 157.0502 | 328.7048 | 173.1 | 59.594 | 601.2578 | 714.7638 | -176.7022 | -63.1962
Contingency (held by STFC)
Total Award | 777.96
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## WP3
WP3 | Approved | Transfers | Actual spend in previous years |  |  | Allocation to completion | Actual spend 2008/9 to end July | Total |  | Variance
| (excluding contingency) |  | (2) |  |  | (4) | (3) | Actual spend (2+3) | Projected spend (2+4) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | 2007/8 | 2008/9 |  | (6) | (7)
Birmingham Effort | 60.2 |  | 0 | 7.2953 | 26.4422 | 24.1 | 2.5 | 36.2375 | 57.8375 | -23.9625 | -2.3625
Cambridge Effort
ICL Effort | 111.1 |  | 0 | 10.909 | 45.0595 | 35.5 | 23.7 | 79.6685 | 91.4685 | -31.4315 | -19.6315
Manchester Effort
RHUL Effort
UCL Effort
University Sub-Total1 | 171.3 |  | 0 | 18.2042 | 71.5018 | 59.6 | 26.2 | 115.906 | 149.306 | -55.394 | -21.994
RAL PPD Effort | 289 |  | 11.54 | 53.61 | 103.5302 | 62.3 | 19.5 | 188.1802 | 230.9802 | -100.8198 | -58.0198
RAL ED/ID Effort | 277.2 |  | 14.38 | 82.32 | 89.9501 | 73.4 | 28.801 | 215.4511 | 260.0501 | -61.7489 | -17.1499
Equipment1 | 206.6 | 15 | 0 | 15.107 | 63 | 40 | 60 | 138.107 | 118.107 | -83.493 | -103.493
Travel | 30.9 |  | 0.49231 | 3.156 | 7.39 | 7 | 0.5 | 11.5384 | 18.0384 | -19.3616 | -12.8616
Consumables 1 | 59.2 |  | 1.228 | 0.017 | 9.5 | 10 | 5.129 | 15.874 | 20.745 | -43.326 | -38.455
Exceptional1
Total (excluding VAT and WA) | 1034.2 |  | 27.6403 | 172.4143 | 344.8721 | 252.3 | 140.13 | 685.0567 | 797.2267 | -364.1433 | -251.9733
Working allowance |  | -15 | [5 empty] | 0 | 0 | 15 | 15
VAT
Total (including VAT & WA) | 1034.2 |  | 27.6403 | 172.4143 | 344.8721 | 252.3 | 140.13 | 685.0567 | 797.2267 | -349.1433 | -236.9733
Contingency (held by STFC)
Total Award | 1034.2
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.
Note: FRS reports additional equipment/consumables spend in 2005/6 of £11.5k that was paid from the previous CALICE grant award.

## WP4
WP4 | Approved | Transfers | Actual spend in previous years |  |  | Allocation to completion | Actual spend 2008/9 to end July | Total |  | Variance
| (excluding contingency) |  | (2) |  |  | (4) | (3) | Actual spend (2+3) | Projected spend (2+4) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | 2007/8 | 2008/9 |  | (6) | (7)
Birmingham Effort
Cambridge Effort
ICL Effort
Manchester Effort | 152.1 |  | 20.31 | 24.249 | 52.4093 | 16.5 | 5.5 | 102.4683 | 113.4683 | -49.6317 | -38.6317
RHUL Effort
UCL Effort
University Sub-Total1 | 152.1 |  | 20.31 | 24.249 | 52.4093 | 16.5 | 5.5 | 102.4683 | 113.4683 | -49.6317 | -38.6317
RAL PPD Effort
RAL ED/ID Effort
Equipment1 | 19.5 |  | 0 | 0 | 2.11 | 0 | 0 | 2.11 | 2.11 | -17.39 | -17.39
Travel | 4.2 |  | 0.49231 | 0.63244 | 1.06 | 2.0153 | 0 | 2.1847 | 4.2 | -2.0153 | 0
Consumables 1 | 9.5 |  | 0 | 0 | 2.11 | 10 | 0 | 2.11 | 12.11 | -7.39 | 2.61
Exceptional1
Total (excluding VAT and WA) | 185.3 |  | 20.8023 | 24.8814 | 57.6893 | 28.5153 | 5.5 | 108.873 | 131.8883 | -76.427 | -53.4117
Working allowance | [7 empty] | 0 | 0 | 0 | 0
VAT
Total (including VAT & WA) | 185.3 |  | 20.8023 | 24.8814 | 57.6893 | 28.5153 | 5.5 | 108.873 | 131.8883 | -76.427 | -53.4117
Contingency (held by STFC)
Total Award | 185.3
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## WP5
WP5 | Approved | Transfers | Actual spend in previous years |  |  | Allocation to completion | Actual spend 2008/9 to end July | Total |  | Variance
| (excluding contingency) |  | (2) |  |  | (4) | (3) | Actual spend (2+3) | Projected spend (2+4) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | 2007/8 | 2008/9 |  | (6) | (7)
Birmingham Effort | 92.3 |  | 3.15 | 32.8286 | 33.169 | 0 |  | 69.1476 | 69.1476 | -23.1524 | -23.1524
Cambridge Effort | 71.86 |  | 0 | 23.11 | 48.9519 | 13.9 | 4.6 | 76.6619 | 85.9619 | 4.8019 | 14.1019
ICL Effort | 29.1 |  | 0 | 10.909 | 12.672 | 0 |  | 23.581 | 23.581 | -5.519 | -5.519
Manchester Effort
RHUL Effort | 123.8 |  | 4.7 | 9.837 | 55.1866 | 11 | 4.8 | 74.5236 | 80.7236 | -49.2764 | -43.0764
UCL Effort | 36.9 |  | 0 | 0 | 20.2224 | 0 |  | 20.2224 | 20.2224 | -16.6776 | -16.6776
University Sub-Total1 | 353.96 |  | 7.85 | 76.6846 | 170.2019 | 24.9 | 9.4 | 264.1365 | 279.6365 | -89.8235 | -74.3235
RAL PPD Effort | [5 empty] | 16 | 5
RAL ED/ID Effort
Equipment1
Travel | 50.2 |  | 3.4461 | 8.2033 | 27.7 | 10 | 2 | 41.3494 | 49.3494 | -8.8506 | -0.8506
Consumables 1 | 4.1 |  | 0 | 0 | 2.11 | 0 | 0 | 2.11 | 2.11 | -1.99 | -1.99
Exceptional1
Total (excluding VAT and WA) | 408.26 |  | 11.2961 | 84.8879 | 200.0119 | 50.9 | 16.4 | 307.5959 | 331.0959 | -100.6641 | -77.1641
Working allowance | [7 empty] | 0 | 0 | 0 | 0
VAT
Total (including VAT & WA) | 408.26 |  | 11.2961 | 84.8879 | 200.0119 | 50.9 | 16.4 | 307.5959 | 331.0959 | -100.6641 | -77.1641
Contingency (held by STFC)
Total Award | 408.26
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## Birmingham
Birmingham
Mikami | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 3.15 | 3.15 | 3.6476 | 3.55 | 3.6854 | 3.49 | 3.9277 | 3.62
WP1 months | 1 | 3.15 | 1 | 3.6476 |  | 0 |  | 0 | 2 | 6.7976 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 | 2 | 7.2953 | 3 | 11.0563 | 3 | 11.7831 | 8 | 30.1347 | 1.5 | 5.5282 | 4.5 | 17.3113
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months | 1 | 3.15 | 9 | 32.8286 | 9 | 33.169 | 7 | 27.4939 | 26 | 96.6415 | 4.5 | 16.5845 | 11.5 | 44.0784
Staley | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.84 | 5.84 | 6.0006 | 5.84 | 6.167 | 5.84 | 6.3364 | 5.84
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 2 | 12.3341 | 2 | 12.6728 | 4 | 25.0069 | 1 | 6.167 | 3 | 18.8398
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electronics techs | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 2.72 | 2.72 | 2.877 | 2.8 | 3.0518 | 2.89 | 3.2224 | 2.97
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 1 | 3.0518 | 2 | 6.4449 | 3 | 9.4967 | 0.5 | 1.5259 | 2.5 | 7.9708
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 1 | 3.15 | 1 | 3.6476 | 0 | 0 | 0 | 0 | 2 | 6.7976 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 2 | 7.2953 | 6 | 26.4422 | 7 | 30.9008 | 15 | 64.6383 | 3 | 13.2211 | 10 | 44.1219
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 1 | 3.15 | 9 | 32.8286 | 9 | 33.169 | 7 | 27.4939 | 26 | 96.6415 | 4.5 | 16.5845 | 11.5 | 44.0784
Sum | 2 | 6.3 | 12 | 43.7715 | 15 | 59.6112 | 14 | 58.3947 | 43 | 168.0774 | 7.5 | 29.8056 | 21.5 | 88.2003
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## Cambridge
Cambridge
Mavromanolakis | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 3.536 | 3.536 | 3.8192 | 3.717 | 4.0793 | 3.863 | 4.3867 | 4.043
WP1 months | 9 | 29.546 | 6 | 23.11 |  | 0 | 3 | 13.16 | 18 | 65.816 | 0 | 0 | 3 | 13.16
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 6 | 23.11 | 12 | 48.9519 |  | 0 | 18 | 72.0619 | 6 | 24.476 | 6 | 24.476
Goodrick | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.77 | 5.77 | 5.9287 | 5.77 | 6.241 | 5.91 | 6.4123 | 5.91
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 2 | 11.425 | 2 | 12.16 | 3 | 19.1 | 1 | 6.6 | 8 | 49.285 | 1.5 | 9.55 | 2.5 | 16.15
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shaw | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 3.5 | 3.5 | 3.7093 | 3.61 | 3.865 | 3.66 | 4.0796 | 3.76
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 3.583 | 2 | 7.566 | 2 | 8 | 2 | 8.1592 | 7 | 27.3082 | 1 | 4 | 3 | 12.1592
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Barham | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 3.19 | 3.19 | 3.3188 | 3.23 | 3.4531 | 3.27 | 3.5805 | 3.3
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 3.177 | 3 | 10.219 | 4 | 14 | 3 | 10.8 | 11 | 38.196 | 2 | 7 | 5 | 17.8
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 9 | 29.546 | 6 | 23.11 | 0 | 0 | 3 | 13.16 | 18 | 65.816 | 0 | 0 | 3 | 13.16
WP2 | 4 | 18.185 | 7 | 29.945 | 9 | 41.1 | 6 | 25.5592 | 26 | 114.7892 | 4.5 | 20.55 | 10.5 | 46.1092
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 6 | 23.11 | 12 | 48.9519 | 0 | 0 | 18 | 72.0619 | 6 | 24.476 | 6 | 24.476
Sum | 13 | 47.731 | 19 | 76.165 | 21 | 90.0519 | 9 | 38.7192 | 62 | 252.6671 | 10.5 | 45.026 | 19.5 | 83.7451
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## ICL
ICL
Magnan | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 3.79 | 3.79 | 3.997 | 3.89 | 4.224 | 4 | 4.4485 | 4.1
WP1 months | 5 | 17.542 | 5 | 18.182 | 2 | 8.448 |  | 0 | 12 | 44.172 | 1 | 4.224 | 1 | 4.224
WP2 months |  | 0 | 1 | 3.636 | 2 | 8.448 | 2 | 8.897 | 5 | 20.981 | 1 | 4.224 | 3 | 13.121
WP3 months |  | 0 | 3 | 10.909 | 5 | 21.12 | 4 | 17.794 | 12 | 49.823 | 2.5 | 10.56 | 6.5 | 28.354
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 3 | 10.909 | 3 | 12.672 | 1 | 4.4485 | 7 | 28.0295 | 1.5 | 6.336 | 2.5 | 10.7845
Zorba | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.97 | 4.97 | 5.2505 | 5.11 | 5.544 | 5.25 | 5.8482 | 5.39
WP1 months | 1 | 4.97 |  | 0 |  | 0 |  | 0 | 1 | 4.97 | 0 | 0 | 0 | 0
WP2 months |  | 0 | 1 | 5.2505 | 2 | 11.088 | 1 | 5.8482 | 4 | 22.1867 | 1 | 5.544 | 2 | 11.3922
WP3 months |  | 0 |  | 0 | 2 | 11.088 | 3 | 17.5445 | 5 | 28.6324 | 1 | 5.544 | 4 | 23.0885
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Price | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 6.93 | 6.93 | 7.3261 | 7.13 | 7.7405 | 7.33 | 8.17 | 7.53
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 | 1 | 7.3261 | 3 | 23.2214 | 2 | 16.3401 | 6 | 46.8876 | 1.5 | 11.6107 | 3.5 | 27.9508
WP3 months |  | 0 |  | 0 | 1 | 7.7405 | 1 | 8.17 | 2 | 15.9105 | 0.5 | 3.8702 | 1.5 | 12.0403
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Clark | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.58 | 4.58 | 4.8395 | 4.71 | 5.111 | 4.84 | 5.3816 | 4.96
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 1 | 5.111 | 2 | 10.7632 | 3 | 15.8742 | 0.5 | 2.5555 | 2.5 | 13.3187
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 6 | 22.512 | 5 | 18.182 | 2 | 8.448 | 0 | 0 | 13 | 49.142 | 1 | 4.224 | 1 | 4.224
WP2 | 0 | 0 | 3 | 16.2126 | 7 | 42.7574 | 5 | 31.0852 | 15 | 90.0553 | 3.5 | 21.3787 | 8.5 | 52.464
WP3 | 0 | 0 | 3 | 10.909 | 9 | 45.0595 | 10 | 54.2717 | 22 | 110.2402 | 4.5 | 22.5298 | 14.5 | 76.8015
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 3 | 10.909 | 3 | 12.672 | 1 | 4.4485 | 7 | 28.0295 | 1.5 | 6.336 | 2.5 | 10.7845
Sum | 6 | 22.512 | 14 | 56.2126 | 21 | 108.937 | 16 | 89.8054 | 57 | 277.467 | 10.5 | 54.4685 | 26.5 | 144.2739
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## Manchester
Manchester
Hughes-Jones | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 5.94 | 5.94 | 6.5246 | 6.35 | 6.5683 | 6.22 | 6.9115 | 6.37
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 5.94 | 2 | 13.0493 | 2 | 13.1366 | 1 | 6.9115 | 6 | 39.0373 | 1 | 6.5683 | 2 | 13.4798
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kelly | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 3.5 | 3.5 | 4.1408 | 4.03 | 6.6528 | 6.3 | 6.9982 | 6.45
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 3.5 | 1 | 4.1408 | 1 | 6.6528 | 1 | 6.9982 | 4 | 21.2919 | 0.5 | 3.3264 | 1.5 | 10.3247
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thompson | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.52 | 5.52 | 6.5246 | 6.35 | 6.5683 | 6.22 | 6.9115 | 6.37
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 5.52 | 1 | 6.5246 | 4 | 26.2733 | 4 | 27.6458 | 10 | 65.9637 | 2 | 13.1366 | 6 | 40.7824
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Snow | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums
Monthly cost | 5.45 | 5.45 | 6.0931 | 5.93 | 6.7373 | 6.38 | 7.3238 | 6.75
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 5.45 | 1 | 6.0931 | 1 | 6.7373 | 1 | 7.3238 | 4 | 25.6041 | 0.5 | 3.3686 | 1.5 | 10.6924
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Freestone | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 3.74 | 3.74 | 4.3977 | 4.28 | 4.7942 | 4.54 | 5.2297 | 4.82
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 3.74 | 1 | 4.3977 | 2 | 9.5885 | 2 | 10.4594 | 6 | 28.1856 | 1 | 4.7942 | 3 | 15.2536
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Elvin | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 2.8 | 2.8 | 3.6168 | 3.52 | 3.4954 | 3.31 | 3.7649 | 3.47
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 2.8 | 1 | 3.6168 | 2 | 6.9907 | 2 | 7.5299 | 6 | 20.9374 | 1 | 3.4954 | 3 | 11.0253
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perry | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 2.8 | 2.8 | 3.6168 | 3.52 | 2.8195 | 2.67 | 3.038 | 2.8
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 2.8 | 1 | 3.6168 | 1 | 2.8195 | 1 | 3.038 | 4 | 12.2743 | 0.5 | 1.4098 | 1.5 | 4.4478
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 2 | 9.44 | 3 | 17.1901 | 3 | 19.7894 | 2 | 13.9097 | 10 | 60.3292 | 1.5 | 9.8947 | 3.5 | 23.8044
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 5 | 20.31 | 5 | 24.249 | 10 | 52.4093 | 10 | 55.9969 | 30 | 152.9651 | 5 | 26.2046 | 15 | 82.2015
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sum | 7 | 29.75 | 8 | 41.4391 | 13 | 72.1987 | 12 | 69.9065 | 40 | 213.2943 | 6.5 | 36.0994 | 18.5 | 106.0059
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## RHUL
RHUL
Wu | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 3.5 | 3.5 | 3.699 | 3.6 | 3.8966 | 3.69 | 4.1121 | 3.79
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 | 3 | 4.837 | 6 | 23.3798 | 15 | 61.6823 | 24 | 89.8991 | 3 | 11.6899 | 18 | 73.3722
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 2 | 4.837 | 6 | 23.3798 | 6 | 24.6729 | 14 | 52.8897 | 3 | 11.6899 | 9 | 36.3628
Salvatore | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.8 | 4.8 | 5.1375 | 5 | 5.3011 | 5.02 | 5.6745 | 5.23
WP1 months | 1 | 4.7 | 1 | 5 |  | 0 |  | 0 | 2 | 9.7 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months | 1 | 4.7 | 1 | 5 | 6 | 31.8067 | 6 | 34.0473 | 14 | 75.554 | 3 | 15.9034 | 9 | 49.9507
Green | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.88 | 5.88 | 6.052 | 5.89 | 6.2304 | 5.9 | 6.4123 | 5.91
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 5.85 | 3 | 18.03 | 4 | 24.9216 | 2 | 12.8247 | 10 | 61.6263 | 2 | 12.4608 | 4 | 25.2855
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 1 | 4.7 | 1 | 5 | 0 | 0 | 0 | 0 | 2 | 9.7 | 0 | 0 | 0 | 0
WP2 | 1 | 5.85 | 6 | 22.867 | 10 | 48.3014 | 17 | 74.507 | 34 | 151.5254 | 5 | 24.1507 | 22 | 98.6577
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 1 | 4.7 | 3 | 9.837 | 12 | 55.1866 | 12 | 58.7202 | 28 | 128.4438 | 6 | 27.5933 | 18 | 86.3135
Sum | 3 | 15.25 | 10 | 37.704 | 22 | 103.488 | 29 | 133.2271 | 64 | 289.6692 | 11 | 51.744 | 40 | 184.9711
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## UCL
UCL
Bartsch | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 3.54 | 3.54 | 3.7709 | 3.67 | 4.0445 | 3.83 | 4.2966 | 3.96
WP1 months | 0.5 | 2 | 0 | 0 |  | 0 |  | 0 | 0.5 | 2 | 0 | 0 | 0 | 0
WP2 months |  | 0 | 0 | 0 | 7 | 28.3114 | 5 | 21.483 | 12 | 49.7944 | 3.5 | 14.1557 | 8.5 | 35.6387
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 0 | 0 | 5 | 20.2224 | 3 | 12.8898 | 8 | 33.1122 | 2.5 | 10.1112 | 5.5 | 23.001
Warren | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.61 | 4.61 | 4.7881 | 4.66 | 5.2483 | 4.97 | 5.4576 | 5.03
WP1 months | 1 | 4.61 | 1 | 4.7881 |  | 0 |  | 0 | 2 | 9.3981 | 0 | 0 | 0 | 0
WP2 months | 2 | 9.22 | 5 | 23.9408 | 6 | 31.4899 | 3 | 16.3727 | 16 | 81.0233 | 3 | 15.745 | 6 | 32.1176
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Postranecky | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.13 | 5.13 | 5.2711 | 5.13 | 6.0192 | 5.7 | 6.1845 | 5.7
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 2 | 10.26 | 4 | 21.0843 | 6 | 36.1152 | 3 | 18.5535 | 15 | 86.013 | 3 | 18.0576 | 6 | 36.6111
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 1.5 | 6.61 | 1 | 4.7881 | 0 | 0 | 0 | 0 | 2.5 | 11.3981 | 0 | 0 | 0 | 0
WP2 | 4 | 19.48 | 9 | 45.0251 | 19 | 95.9165 | 11 | 56.4091 | 43 | 216.8307 | 9.5 | 47.9582 | 20.5 | 104.3674
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 5 | 20.2224 | 3 | 12.8898 | 8 | 33.1122 | 2.5 | 10.1112 | 5.5 | 23.001
Sum | 5.5 | 26.09 | 10 | 49.8132 | 24 | 116.1389 | 14 | 69.299 | 53.5 | 261.341 | 12 | 58.0694 | 26 | 127.3684
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## RAL PPD
RAL PPD
Tyndel | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 6.5 | 6.5 | 6.6787 | 6.5 | 6.864 | 6.5 | 7.0525 | 6.5
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 1 | 6.5 | 1 | 6.6787 | 1 | 6.864 | 1 | 7.0525 | 4 | 27.0953 | 0.5 | 3.432 | 1.5 | 10.4845
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Villani | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 6.5 | 6.5 | 6.6787 | 6.5 | 6.864 | 6.5 | 7.0525 | 6.5
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 5 | 32.5 | 5 | 33.3937 | 5 | 34.32 | 5 | 35.2625 | 20 | 135.4762 | 2.5 | 17.16 | 7.5 | 52.4225
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stanitski | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.92 | 4.92 | 5.0553 | 4.92 | 5.1955 | 4.92 | 5.3382 | 4.92
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 12 | 62.3462 | 12 | 64.0584 | 24 | 126.4046 | 6 | 31.1731 | 18 | 95.2315
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 6 | 39 | 6 | 40.0725 | 18 | 103.5302 | 18 | 106.3734 | 48 | 288.9761 | 9 | 51.7651 | 27 | 158.1385
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sum | 6 | 39 | 6 | 40.0725 | 18 | 103.5302 | 18 | 106.3734 | 48 | 288.9761 | 9 | 51.7651 | 27 | 158.1385
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## RAL ID
RAL ID
Turchetta | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 10.89 | 10.89 | 11.508 | 11.2 | 12.144 | 11.5 | 12.8247 | 11.82
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 1 | 10.89 | 1 | 11.508 | 1 | 12.144 | 1 | 12.8247 | 4 | 47.3667 | 0.5 | 6.072 | 1.5 | 18.8967
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crooks | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.69 | 5.69 | 6.0828 | 5.92 | 6.4838 | 6.14 | 6.9006 | 6.36
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 3 | 17.07 | 12 | 72.9936 | 12 | 77.8061 | 9 | 62.1054 | 36 | 229.9751 | 6 | 38.903 | 15 | 101.0084
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 4 | 27.96 | 13 | 84.5016 | 13 | 89.9501 | 10 | 74.9301 | 40 | 277.3418 | 6.5 | 44.975 | 16.5 | 119.9051
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sum | 4 | 27.96 | 13 | 84.5016 | 13 | 89.9501 | 10 | 74.9301 | 40 | 277.3418 | 6.5 | 44.975 | 16.5 | 119.9051
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## Other
|  | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Total |  | Left | Left for
|  | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Allocated | Actual | in budget | 2008/9
Equipment | WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| WP2 | 11 | 0 | 36.99 | 8.114 | 65 | 24 | 16.28 |  | 118.1 | 32.114 | 85.986 | 44.986
| WP3 | 0 | 0 | 3.08 | 15.107 | 63 | 34.8 | 108.5 |  | 206.6 | 49.907 | 156.693 | 128.493
| WP4 | 0 | 0 | 0 | 0 | 2.11 | 0 | 17.36 |  | 19.5 | 0 | 19.5 | 17.39
| WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Total | 11 | 0 | 40.07 | 23.221 | 130.11 | 58.8 | 142.14 | 0 | 344.2 | 82.021 | 262.179 | 190.869
Consumables | WP1 | 6 | 0.407 | 5.14 | 3.875 | 0 | 2.2 | 0 |  | 11.1 | 6.482 | 4.618 | 6.818
| WP2 | 4 | 0 | 9.25 | 13.908 | 6.34 | 1.69 | 0 |  | 19.6 | 15.598 | 4.002 | -0.648
| WP3 | 2 | 1.228 | 1.03 | 0.017 | 9.5 | 5 | 46.66 |  | 59.2 | 6.245 | 52.955 | 48.455
| WP4 | 0 | 0 | 3.08 | 0 | 2.11 | 0 | 4.34 |  | 9.5 | 0 | 9.5 | 7.39
| WP5 | 2 | 0 | 0 | 0 | 2.11 | 0 | 0 |  | 4.1 | 0 | 4.1 | 1.99
| Total | 14 | 1.635 | 18.5 | 17.8 | 20.06 | 8.89 | 51 | 0 | 103.5 | 28.325 | 75.175 | 64.005
Travel | WP1 | 34 | 16.7384 | 55.49 | 34.0718 | 32.2 | 20.9 | 0 |  | 111.7 | 71.7102 | 39.9898 | 28.6898
| WP2 | 6 | 2.9538 | 6.17 | 3.7885 | 9.5 | 6.17 | 3.26 |  | 24.9 | 12.9123 | 11.9877 | 8.6577
| WP3 | 1 | 0.49231 | 5.14 | 3.156 | 7.39 | 4.9 | 17.36 |  | 30.9 | 8.5484 | 22.3516 | 19.8616
| WP4 | 1 | 0.49231 | 1.03 | 0.63244 | 1.06 | 0.6 | 1.09 |  | 4.2 | 1.7247 | 2.4753 | 2.0153
| WP5 | 7 | 3.4461 | 13.36 | 8.2033 | 27.7 | 18 | 10.85 |  | 50.2 | 29.6494 | 20.5506 | 10.8506
| Total | 49 | 24.123 | 81.19 | 49.852 | 77.85 | 50.57 | 32.56 | 0 | 221.9 | 124.545 | 97.355 | 70.075
Travel
| General |  | 9.741 |  | 5.98
| Birmingham |  | 1.462 |  | 8.007
| Cambridge |  | 1.546 |  | 11.235
| Imperial |  | 2.346 |  | 9.555
| Manchester |  | 3.404 |  | 2.585
| RAL-TD |  | 0 |  | 0
| RAL-PPD |  | 0 |  | 0.564
| RHUL |  | 1.878 |  | 8.497
| UCL |  | 3.746 |  | 3.429
| Total | 49 | 24.123 | 81.19 | 49.852