## Sheet1
PARTICLE PHYSICS PROJECTS RISK PROFORMA
Ref | Risk Description | Potential impact on project | Inherent Risk Score |  |  | Existing Controls | Mitigating factors | Residual risk score |  |  | Comment | Proposed Action
|  |  | L | I | L×I |  |  | L | I | L×I
WP1.1 | Failure of ECAL wafer fabrication | Loss of some ECAL layers leading to less useful data | 2 | 3 | 6 | Non-UK: Sourcing wafers from four manufacturers | Perform studies of layer arrangement to minimise impact of missing layers | 2 | 2 | 4
WP1.2 | Failure of AHCAL or DHCAL systems | Loss of data for simulation comparisions | 2 | 2 | 4 | Non-UK: Technical Board reviews very six months |  | 2 | 2 | 4
WP1.3 | Extended beam test period required due to problems with calorimeters, beams or DAQ | Higher travel costs | 2 | 1 | 2 | Thorough testing of equipment before shipping. Visit beam areas and understand environment before beam test |  | 2 | 1 | 2
WP2.1 | Failure of VFE ASIC production so no chips available for PCB test | Non-verification of ASIC by time of TDR | 1 | 2 | 2 | Non-UK: Review ASIC design before each fabrication round |  | 1 | 2 | 2
WP2.2 | Not able to find manufacturer for 1.5m PCBs | Study not completed in time for TDR | 2 | 2 | 4 |  | Rely on smaller PCB stitching techniques | 2 | 2 | 4
WP2.3 | Delays in sourcing components | Delays in tests | 1 | 2 | 2 |  | Continue work with partially complete engineering version of boards | 1 | 2 | 2
WP3.1 | Failure of sensor fabrication round | Three to four month delay in schedule and extra cost to remake | 2 | 2 | 4 | Regular design reviews according to ISO9000 specifications | Prepare tests before fabrication complete so major errors can be identified immediately | 2 | 2 | 4
All.1 | Delays/problems with RA appointments | Less impact on projects | 2 | 1 | 2 | Schedule recruitment period well in advance | Three of the five new project RAs are now in post | 2 | 1 | 2
All.2 | Loss of staff with required skills | Loss of expertise mid-way, causing delays | 3 | 2 | 6 |  | Ensure personnel work closely with othe UK colleagues so no one individual has critical knowledge | 3 | 2 | 6
All.3 | Illness of staff in critical positions | Reallocation of effort causing delays | 2 | 2 | 4 |  | As above | 2 | 2 | 4
L = Likelihood on scale of 1, 2 ,3 4 where 1 is low.
I = Impact on scale of 1, 2, 3, 5 where 1 is low.
High risk is a score greater than 8